## Backlog
Product Backlog Project Name
Done
User Story Id | User Story Name | Assigned To | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_01 | User Registration |  | User | Ability of the system to enroll new users. | 1. When a user opens the screen, a registeration form appears. 2. User should fill up required information. 3. The details provided by the user are then stored to database. | 1 | 1
US_02 | User Authentication |  | User | Ability of the system to authenticate and let the user login. | 1. System must validate user credentials (email and password). 2. If user provides incorrect credentials then he/she could not proceed further. | 1 | 2
US_03 | User Profile |  | User | Ability of the system to allow the user to check more about his profile. | 1. System displays user details to the logged-in user. 2. System provides users accessiblity to change data. | 2 | 1
US_04 | User Home |  | User | Ability of the system to provide a dashboard to user | 1. System displays a home landing page to the logged-in user 2. System provides users provision to trigger SOS | 1 | 3
US_05 | Request an Ambulance |  | User | Ability of the system to send a SOS signal in order to find an ambulance nearby. | 1.System must look up for available ambulances nearby to the user. 2.System must book the nearest one. | 2 | 2
US_06 | Feedback |  | User | Ability of the system to get feedback from the user. | 1.Get the feedback from user on the booking details. 2.Display it to all the users. | 1 | 5
US_07 | Calculate ETA |  | System | Ability of the system to calculate the estimated time of arrival. | 1. System calculates minimum estimated time of arrival using shortest path available. 2. The system displays the above calculated ETA. | 2 | 3
US_08 | Display Booking Summary |  | System | Ability of the system to display the pickup and drop location. | 1.System must fetch the nearest hospital around the user. 2.System must display the selected hospital details to the user. | 2 | 5
US_09 | Display Ambulance Details |  | System | Ability of the system to display the ambulance details. | 1. System fetches details of the ambulance from the database. 2. Displays the above details to the User. | 2 | 8
US_10 | Traffic Admin Login |  | Traffic Admin | Ability of the system to authenticate and let the traffic admin login. | 1. System must validate Admin's credentials (email and password). 2. If traffic admin provides incorrect credentials then he/she could not proceed further. | 1 | 13
US_11 | Notify Traffic Admin |  | Traffic Admin | Ability of the System to notify admin of the incoming ambulance. | 1. As the admin gets notified of the incoming ambulance, he then establishes green coridor. 2. A green coridor provides ambulance unrestricted passage. | 2 | 13
US_12 | Logout |  | User | Ability of the system to allow the user to log-out. | 1. User is logged off from the account. | 1 | 8

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 100 | 95 | 37% | -95 | 75
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000